Hotel Management System

Project Proposal

A cloud-based, multi-property reservation, billing and operations platform

Prepared for: [Client / Hotel Group Name]

Prepared by: Disura

Date: July 2026

Version: 1.0

Status: Draft for client review

# Revision History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 0.1 | 15 Jun 2026 | Disura | Initial draft |
| 1.0 | 01 Jul 2026 | Disura | First version issued for client review |

# Table of Contents

# 1. Executive Summary

This document proposes the design, development, and deployment of a Hotel Management System (HMS) intended to replace manual or spreadsheet-based front-desk operations with a single, secure, cloud-based platform. The system will manage reservations, room inventory, guest profiles, billing, housekeeping, staff access, and reporting across one or more properties from a unified dashboard.

The proposed solution is built on a modern, cost-effective technology stack (React, Node.js, PostgreSQL) chosen specifically to balance total cost of ownership, long-term maintainability, and production-grade security, while remaining flexible enough to scale from a single boutique hotel to a multi-branch hotel group.

This proposal covers the business case, project scope, methodology, timeline, cost estimate, team structure, risk assessment, and success criteria for the engagement.

# 2. Background and Problem Statement

Many small and mid-sized hotels continue to rely on paper registers, spreadsheets, or disconnected point-of-sale tools to manage reservations, billing, and housekeeping. This creates several recurring problems:

- Double-bookings caused by manually cross-checking availability across channels.

- Delayed or inaccurate billing due to manually tallied guest folios.

- No real-time visibility into occupancy, revenue, or housekeeping status across properties.

- Limited or no audit trail for cancellations, refunds, and rate overrides.

- Inability to safely delegate access — staff often share a single login with full privileges.

- No structured way to expand to a second or third property without duplicating manual processes.

The proposed HMS directly addresses each of these gaps through a purpose-built, role-based, multi-property platform.

# 3. Project Objectives

- Provide a single source of truth for room availability, eliminating double-bookings through database-enforced booking rules.

- Automate guest billing (folio management) from check-in through checkout, including itemised charges and integrated payment collection.

- Introduce role-based access control (Owner, Manager, Front Desk, Housekeeping, Accountant) so staff only see and do what their role permits.

- Give management real-time occupancy, revenue, and performance reporting without manual data compilation.

- Support multiple properties/branches from one account for hotel groups planning to expand.

- Meet modern security and data-protection expectations, including encrypted credentials, audit logging, and secure payment handling.

- Deliver a system that is cost-effective to run and straightforward for the client's own staff or a small IT team to maintain going forward.

# 4. Scope of Work

## 4.1 In Scope

- Web-based staff dashboard (reservations, guest profiles, billing, housekeeping, reporting, settings).

- Public-facing booking widget for direct guest reservations.

- Role-based authentication and authorization for staff accounts.

- Folio and billing module with integrated payment gateway (Stripe / PayHere).

- Housekeeping status tracking (clean / dirty / inspected / out-of-order).

- Multi-property support with property-level data isolation.

- Operational reports: occupancy, ADR, RevPAR, daily revenue, night-audit summary.

- Deployment to a managed cloud environment with backups and monitoring.

- User manuals and technical handover documentation.

## 4.2 Out of Scope (Phase 1)

- Direct two-way synchronisation with OTAs (Booking.com, Agoda, Expedia) — planned as a Phase 2 enhancement.

- Native mobile applications for guests (a mobile-responsive web app is included; native iOS/Android apps are a future phase).

- Point-of-sale for restaurant/spa outlets beyond basic folio charge posting.

- Accounting-system integration (e.g., QuickBooks/Xero export) — can be scoped separately.

# 5. Proposed Technology Stack (Summary)

A full technical breakdown is provided in the accompanying Software Design Document. In summary:

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend | React 19 + TypeScript, Tailwind CSS | Fast, maintainable UI; large talent pool for future maintenance |
| Backend | Node.js + Express, TypeScript | Single language across stack lowers long-term maintenance cost |
| Database | PostgreSQL | Strong transactional integrity; prevents double-booking at the data layer |
| Cache / Queue | Redis | Session storage, rate limiting, background job queue |
| Hosting | DigitalOcean / AWS (managed) | Cost-effective, scales as the client grows |
| Payments | Stripe or PayHere | PCI compliance offloaded to a certified provider |

# 6. Development Methodology

The project will follow an iterative, Agile-influenced approach delivered in short cycles (sprints), allowing the client to review working software early and often rather than waiting for a single final delivery.

- Requirements gathering and sign-off (Software Requirements Specification).

- System and database design (Software Design Document, Database Design Document, UI/UX Design Document).

- Iterative development in 2-week sprints, each ending in a client demo.

- Continuous testing (unit, integration, and user acceptance testing).

- Staged deployment: development → staging → production.

- Post-launch support and warranty period.

# 7. Project Timeline

| Phase | Duration | Key Deliverables |
| --- | --- | --- |
| Requirements & design | 2 weeks | SRS, SDD, Database Design, UI/UX Design sign-off |
| Core development – reservations & rooms | 3 weeks | Room inventory, availability engine, booking flow |
| Core development – billing & payments | 2 weeks | Folio management, payment gateway integration |
| Core development – admin & reporting | 2 weeks | RBAC, housekeeping module, reports |
| Testing & UAT | 2 weeks | Bug fixes, client user-acceptance sign-off |
| Deployment & training | 1 week | Production go-live, staff training, documentation handover |
| Warranty support | 4 weeks post-launch | Bug fixes and minor adjustments at no extra cost |

# 8. Cost Estimate

The figures below are indicative and will be finalised once the SRS is signed off. Hosting costs are recurring and separate from the one-time development cost.

| Item | Estimate |
| --- | --- |
| Requirements, design & documentation | [Amount] |
| Core development (reservations, billing, RBAC, reporting) | [Amount] |
| Payment gateway integration | [Amount] |
| Testing, UAT support & deployment | [Amount] |
| Training & documentation handover | [Amount] |
| One-time development total | [Amount] |
| Recurring: cloud hosting & backups (monthly) | USD 60–300 depending on scale |
| Recurring: payment gateway fees | Per-transaction, set by provider (e.g., 2.9% + fixed fee) |

# 9. Team and Responsibilities

| Role | Responsibility |
| --- | --- |
| Developer (Disura) | Full-stack development, architecture, deployment, security hardening |
| Client stakeholder | Requirements sign-off, UAT participation, content and branding assets |
| Hotel operations lead | Validation of reservation, folio and housekeeping workflows against real operations |

# 10. Risk Assessment

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Requirements change mid-development | Medium | Medium | Formal sign-off of SRS before development; change requests tracked separately |
| Payment gateway approval delays | Medium | Medium | Apply for gateway merchant account in parallel with development |
| Data loss or corruption | Low | High | Automated daily backups, point-in-time recovery on managed database |
| Double-booking under concurrent load | Low | High | Database-level exclusion constraints, not just application checks |
| Staff resistance to new system | Medium | Medium | Hands-on training sessions and a simple, familiar UI |

# 11. Success Criteria

- Zero double-bookings recorded during the first 90 days in production.

- Front-desk staff can complete a check-in and check-out without developer assistance after training.

- Daily/monthly occupancy and revenue reports are available without manual spreadsheet work.

- All payment transactions are reconciled automatically against folios.

- System uptime of 99.5% or higher outside of scheduled maintenance windows.

# 12. Conclusion

This proposal outlines a pragmatic, cost-effective path to replacing manual hotel operations with a secure, scalable management system. The accompanying Software Requirements Specification, Software Design Document, Database Design Document, and UI/UX Design Document provide the detailed technical basis for this proposal and are intended to be reviewed and approved alongside it.

We welcome the opportunity to discuss this proposal further and adjust scope, timeline, or budget to best fit the client's priorities.